## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
TEAM DETAILS
| Table 1 | TEAM DETAILS
TEAM DETAILS
| Table 1 | TEAM DETAILS
BACKLOG
| Table 1 | BACKLOG
SPRINT 1
| Table 1 | SPRINT 1
SPRINT 2
| Table 1 | SPRINT 2
SPRINT 3
| Table 1 | SPRINT 3
SPRINT 4
| Table 1 | SPRINT 4
User stories
| Table 1 | User stories
Sprint -1 Burdown Chart
| Table 1 | Sprint -1 Burdown Chart
Sprint -2 BurnDown Chart
| Table 1 | Sprint -2 BurnDown Chart
Sprint-3 BurnDown Chart
| Table 1 | Sprint-3 BurnDown Chart

## TEAM DETAILS
Initials | First | Last | Email | GitHub Username
VV | Venkat Vamsi | Devadula | vdevadul@stevens.edu | Vamsi920
NV | Nihash | Veeramachaneni | nveerama@stevens.edu | Nihash25
SK | Sai Krishna | Thummala | Sthummal@stevens.edu | SaiKrishnaThummala
GitHub Repository : cs555tm052022Fall

## BACKLOG
Story ID | Story Name | Story Description
US01 | Valid Dates | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Valid Birth before marriage | Birth should occur before marriage of an individual
US03 | Valid Birth before death | Birth should occur before death of an individual
US05 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US04 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less than 100 years old | Death should be less than 100 years after birth for dead people, and current date should be less than 100 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)

## SPRINT 1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Testing
US01 | Valid Dates | NV | Completed | 45 | 65 | 15 | 80 | Done | Done
T01.01 | Store the required date | NV | Completed |  |  |  |  | Done | Done
T01.02 | Store the current date | NV | Completed |  |  |  |  | Done | Done
T01.03 | Validate by comparing the two dates | NV | Completed |  |  |  |  | Done | Done
US03 | Valid Birth before death | NV | Completed | 65 | 90 | 20 | 65 | Done | Done
T03.01 | Check the living status of the person | NV | Completed |  |  |  |  | Done | Done
T03.02 | Store the date of birth | NV | Completed |  |  |  |  | Done | Done
T03.03 | Store the date of death | NV | Completed |  |  |  |  | Done | Done
T03.04 | Perform validation to see whether date of death is after the birth date | NV | Completed |  |  |  |  | Done | Done
US06 | Divorce before Death | SK | Completed | 85 | 120 | 70 | 100 | Done | Done
T06.01 | Check the living status of the person | SK | Completed |  |  |  |  | Done | Done
T06.02 | Check and store the martial status | SK | Completed |  |  |  |  | Done | Done
T06.03 | Store the date of death | SK | Completed |  |  |  |  | Done | Done
T06.04 | Store the date of divorce | SK | Completed |  |  |  |  | Done | Done
T06.05 | Perform validation to see whether date of death is after the date of divorce | SK | Completed |  |  |  |  | Done | Done
US07 | Less than 100 years old | SK | Completed | 75 | 80 | 50 | 70 | Done | Done
T07.01 | Store the date of birth | SK | Completed |  |  |  |  | Done | Done
T07.02 | Store the current date | SK | Completed |  |  |  |  | Done | Done
T07.03 | Calculate the age by comparing the two dates and validate that age is not more than 100 | SK | Completed |  |  |  |  | Done | Done
US05 | Marriage before divorce | VV | Completed | 90 | 120 | 60 | 75 | Done | Done
T05.01 | Check the living status of the person | VV | Completed |  |  |  |  | Done | Done
T05.02 | Check and store the martial status | VV | Completed |  |  |  |  | Done | Done
T05.03 | Store the date of death | VV | Completed |  |  |  |  | Done | Done
T05.04 | Store the date of marriage | VV | Completed |  |  |  |  | Done | Done
T05.05 | Perform validation to see whether date of marraige is after the date of divorce | VV | Completed |  |  |  |  | Done | Done
US08 | Birth before Marriage of Parents | VV | Completed | 100 | 110 | 100 | 45 | Done | Done
T08.01 | Store the date of birth | VV | Completed |  |  |  |  | Done | Done
T08.02 | Retrieve parents Details | VV | Completed |  |  |  |  | Done | Done
T08.03 | Store the date of marriage of parents | VV | Completed |  |  |  |  | Done | Done
T08.04 | Validate to see whether date of birth is before the date of marriage for the parents | VV | Completed |  |  |  |  | Done | Done
Sprint Results:
Keep Doing:
Collaborative Work between the teammates
Common meeting to discuss the roadblocks and help required for the teammates if necessary
Avoid:
Devating from the scope of user story
Delays in the start of sprint work

## SPRINT 2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Testing
US04 | Marriage before death | NV | Completed | 20 | 65 | 15 | 50 | Done | Done
T04.01 | Check the living status of the person | NV | Completed |  |  |  |  | Done | Done
T04.02 | Check and store the martial status | NV | Completed |  |  |  |  | Done | Done
T04.03 | Store the date of death | NV | Completed |  |  |  |  | Done | Done
T04.04 | Store the date of marraige | NV | Completed |  |  |  |  | Done | Done
T04.05 | Perform validation to see whether date of marraige is after the date of divorce | NV | Completed |  |  |  |  | Done | Done
US10 | Marriage after age of 14 | NV | Completed | 15 | 90 | 18 | 60 | Done | Done
T10.01 | Check the living status of the person | NV | Completed |  |  |  |  | Done | Done
T10.02 | Store the date of birth | NV | Completed |  |  |  |  | Done | Done
T10.03 | Calculate Age | NV | Completed |  |  |  |  | Done | Done
T10.04 | Store the date of Marraige | NV | Completed |  |  |  |  | Done | Done
T10.05 | Perform validation to see whether marriage after the age of 14 | NV | Completed |  |  |  |  | Done | Done
US08 | Birth before marriage of parents | SK |  | 15 | 120
T08.01 | Check and store birth | SK
T08.02 | Check and store marital status date of parents | SK
T08.03 | Compare both | SK
US09 | Birth before death of parents | SK |  | 22 | 80
T09.01 | Store the date of birth | SK
T09.02 | Check and store death of mother | SK
T09.03 | Check and store death of Father | SK
T09.04 | Compare birth with smallest date of death of parents | SK
US11 | No bigamy | VV | Completed | 20 | 120 | 20 | 40 | Done | Done
T011.01 | Check the living status of the person | VV | Completed |  |  |  |  | Done | Done
T011.01 | Check and store the martial status | VV | Completed |  |  |  |  | Done | Done
T011.01 | Store the date of marriage | VV | Completed |  |  |  |  | Done | Done
T011.01 | Store the marital status of the spouse | VV | Completed |  |  |  |  | Done | Done
T011.01 | Perform validation to see whetherthere is a bigamy | VV | Completed |  |  |  |  | Done | Done
US12 | Parents not too old | VV | Completed | 18 | 110 | 15 | 110 | Done | Done
T12.01 | Store the date of birth | VV | Completed |  |  |  |  | Done | Done
T12.02 | Retrieve parents Details | VV | Completed |  |  |  |  | Done | Done
T12.03 | Store the date of marriage of parents and birth details | VV | Completed |  |  |  |  | Done | Done
T12.04 | Validate to see whether date of birth of parents and children are not spaced apart | VV | Completed |  |  |  |  | Done | Done
Sprint Results:
Keep Doing:
Collaborative Work between the teammates
Helping the team when a person from the team is looking for help
Common meeting to discuss the roadblocks and help required for the teammates if necessary
Avoid:
Devating from the scope of user story
Delays in testing of the user stories

## SPRINT 3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act. Size | Act. Time | Completed | Testing
US13 | All Male members last names | NV | Completed | 25 | 75 | 15 | 60 | Done | Done
T13.01 | Check the name of the family | NV | Completed |  |  |  |  | Done | Done
T13.02 | Check the gender of the person | NV | Completed |  |  |  |  | Done | Done
T13.03 | Store the name of parent and sibling | NV | Completed |  |  |  |  | Done | Done
T13.04 | Perform validation to see whether the last name | NV | Completed |  |  |  |  | Done | Done
US18 | Siblings should not marry | NV | Completed | 15 | 90 | 18 | 65 | Done | Done
T18.01 | Check the martial status of the person | NV | Completed |  |  |  |  | Done | Done
T18.02 | Check the martial status of the sibling | NV | Completed |  |  |  |  | Done | Done
T18.03 | Store the matial details details of the siblings | NV | Completed |  |  |  |  | Done | Done
T18.04 | Perform validation to see whether the siblings are partners to each other | NV | Completed |  |  |  |  | Done | Done
US13 | Siblings spacing | SK |  | 15 | 120
T13.01 | Check and store birth details | SK
T13.02 | Check and store birth details of the sibling | SK
T13.03 | Compare both to see whether siblings are born 8 months apart | SK
US14 | Multiple births <= 5 | SK |  | 22 | 80
T14.01 | Check and store birth details | SK
T14.02 | Check and store birth details of the sibling | SK
T14.03 | Check to see whether more than one sibling is born on the same date | SK
T14.04 | Validate to see that less than 5 siblings are born on a same date | SK
US17 | No marriages to descendants | VV | Completed | 20 | 120 | 15 | 80 | Done | Done
T17.01 | Check the martial status of the person | VV | Completed |  |  |  |  | Done | Done
T17.02 | Check the martial status of the parents | VV | Completed |  |  |  |  | Done | Done
T17.03 | Store the marital status of the person and parents | VV | Completed |  |  |  |  | Done | Done
T17.04 | Perform validation to see whether the parents and children are partners to each other | VV | Completed |  |  |  |  | Done | Done
US19 | First cousins should not marry | VV | Completed | 18 | 110 | 24 | 100 | Done | Done
T19.01 | Check the martial status of the person | VV | Completed |  |  |  |  | Done | Done
T19.02 | Check the martial status of the cousin | VV | Completed |  |  |  |  | Done | Done
T19.03 | Store the date of marriage of the person and cousin | VV | Completed |  |  |  |  | Done | Done
T19.04 | Perform validation to see whether cousins are partners to each other | VV | Completed |  |  |  |  | Done | Done
Sprint Results:
Keep Doing:
Collaborative Work between the teammates
Common meeting to discuss the roadblocks and help required for the teammates if necessary
Avoid:
Devating from the scope of user story
Delays in the start of sprint work

## SPRINT 4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act. Size | Act. Time | Completed | Testing
US22 | Unique IDs | NV |  | 25 | 75
T22.01 | Store the ID of the person | NV
T22.02 | Perform validation to see whether the ID is unique fro all | NV
US29 | List deceased | NV |  | 15 | 90
T29.01 | Check the living status of the person | NV
T29.02 | Add to the list if the person is deceased | NV
T29.03 | Display the list | NV
US13 | Siblings spacing | SK |  | 15 | 120
T13.01 | Check and store birth details | SK
T13.02 | Check and store birth details of the sibling | SK
T13.03 | Compare both to see whether siblings are born 8 months apart | SK
US14 | Multiple births <= 5 | SK |  | 22 | 80
T14.01 | Check and store birth details | SK
T14.02 | Check and store birth details of the sibling | SK
T14.03 | Check to see whether more than one sibling is born on the same date | SK
T14.04 | Validate to see that less than 5 siblings are born on a same date | SK
US23 | Unique name and birth date | VV |  | 20 | 120 | 18 | 75 | Done | Done
T23.01 | Store the name of the person | VV
T23.02 | Store the birth date of the person | VV
T23.03 | Perform validation to see whether the name and birth date are unique | VV
US31 | List living single | VV |  | 18 | 110 | 20 | 100 | Done | Done
T31.01 | Check the martial status of the person | VV
T31.02 | Check the living status of the person | VV
T31.03 | Add to the list if the person is alive and single | VV
Sprint Results:
Keep Doing:
Avoid:

## User stories
Table 1

## Sprint -1 Burdown Chart
Date | Planned Work | Actual Work Remaining
Day-1 | 6 | 6
Day-3 | 4 | 5
Day-5 | 4 | 5
Day-7 | 3 | 3
Day-9 | 2 | 2

## Sprint -2 BurnDown Chart
Date | Planned Work | Actual Work Remaining
Day-1 | 6 | 6
Day-3 | 5 | 4
Day-5 | 5 | 4
Day-7 | 4 | 3
Day-9 | 2 | 2

## Sprint-3 BurnDown Chart
Date | Planned Work | Actual Work Remaining
Day-1 | 6 | 6
Day-3 | 5 | 4
Day-5 | 5 | 4
Day-7 | 4 | 3
Day-9 | 2 | 2